## Slide 1: Operational
AVETRA 2015
Division Industry of Industry Vocational Training and Access Education
Notes: the road to dual-sector
too complicated symposium, paper

## Slide 2: Dual Sector Project
“The Transformation of CQUniversity Australia into Queensland’s first Dual Sector University”
Commonwealth SAF $74m
State $120m assets, funding, staff
University contribution - repositioning
Notes: VC Renewal Plan 2009
    Becoming sustainable
    Becoming a strong regional university
    Becoming ‘a truly great university’ – and Australia’s most engaged
Idea 2010 – Research DS in Australia and Internationally
Application 2011- Due Diligence
Political Change
SAF Agreement May 2013
Signed September 2013- Merger and Transfer Agreement
To deliver Dual Sector 2014 – Less than a year

## Slide 3: Structural Adjustment Fund
EIF Funding Agreement $49m
  Capital and Infrastructure- Resources
HESA Grant $29m
  Operational
Notes:   Alone, without the merger 200 roles created within the program to deliver
  Capacity and capability building, secondments, contracts

## Slide 4: Dual-sector: how?
Review of existing Dual Sector models
Context TAFE Reform
Merger with Central Queensland Institute of TAFE
Shrink or grow culture
  Established brands
  Existing talent, resources & infrastructure
Notes: Central Queensland region very unique set of opportunities and challenges
harness ‘the power of place’, and create a purpose-built university for Central Queensland
A dual-sector model:
  Meet the mining / infrastructure skills demand in the region
  Improve engagement with industry (read: employers / investors)
  Help local people realise their ambitions
  Increase participation across VET and degree programs, and manage transitions between the two under one roof
How do we get there?
Rather than building our own dual-sector institution from scratch, we have opted to leverage the opportunity that already exists in the region
– there is strength in numbers:
  Our regional footprint is twice the size of Victoria – that’s a lot of ground to cover!
  More sites equals more study options – the addition of TAFE sites would increase our coverage across this vast region
  Combined resources (human, financial & otherwise) improves our capacity to “do things better”
CQTAFE cuts and deliver core
CQU Growth
Equally, there is strength in utilising two existing “trusted” brands, rather than create a new one from scratch
And, it makes sense to take advantage of the talent, resources & infrastructure that already exists, rather than grow it organically

## Slide 5: Starting Point
Negotiation with State Government
Funding from Federal Government
Communicate
Local Industry and Community
Operations- Getting the ducks in a row
Notes: knitting fog…. herding cats, feral
The first step is negotiation with the State Government
Heads of agreement
Due diligence
Finalising terms – merger agreement
QLD Cabinet and CQUni Council approval
Complementing this is a 74m SAF/EIF funding bid from the Federal Government that will enable the merger
Bricks & mortar
Systems, processes & people
Product
Once this is achieved...
Communication is the next step – and perhaps the most crucial
Every step of the way
Filling the void of misinformation and speculation
Talking to people in both organisations – consistent messages, reassurances wherever possible
“Selling the message” externally – media, stakeholders, industry, government, prospective students
We also have to “get the ducks in a row”
Establish tangible pathways between VET and degree courses and programs
Marry up the systems – IT, payroll, policies & procedures, HR
Figure out what we’re going to call the thing!
...all before we can “open up shop”
And in less than a year

## Slide 6: Governance
Operational Unification - Merger
University Council Resolution
Ministerial sign off
Merger and Transfer Board
SAF Steering Committee
Implementation Group
Notes: New to CQU and STATE systems and changes at their end
Operational Unification
Merger and Transfer Board
First milestone Merger Agreement need a board CQU, State, CQTAFE
Merger by 1 July 2014 (or December 2014? – implications and risk) own the risk
SAF Steering Committee Complex projects from Infrastructure to Operations

## Slide 7: Conditions Precedent
By May 2014:
TAFE Queensland Act Dual Sector Amendment Bill 2014 and Regulation
Asset valuations and covenants
RTO, ASQA, TEQSA, DoE, DETE
Funding Agreement
Successor in law - contracts
Structure – safe transfer of all staff
Notes: Lawyers, DETE, Council negotiations led by DVC
CFO DVC Finance Planning and DVC International and Services not just the VET Division
Negotiate asset transfer with enough flexibility for growth and protecting state assets

## Slide 8: Mechanism
Division Industry Vocational Training and Access Education (DIVTAE)
Change management strategy
Develop a new structure
Key operational areas to merge into university structure
Notes: Strategy- inclusive
Integrate or not to integrate?
Pragmatic – reporting to Minister influences
One step at a time
Growth and quality
Nervousness regarding future, Growth requires staff
Signal change without loosing the valuable elements of TAFE
The name – in regulation permitted to use the protected Term
University structure and nomenclature PVC TAFE, Voc Deans, VOC Schools
Add
320 TAFE staff
Align to existing CQU Systems 100 staff

## Slide 9: Transitional Structure
DVC IVET (Office of)
Division Industry Vocational Training and Access Education (DIVTAE)
University Council
Vice Chancellor
Higher Education
International and Services Finance and Planning
Governance and Student Services
Engagement
Business Performance Directorate:
Finance and Planning, Contracts , Dual Sector & Projects Office
User Choice/VET FEE Help
DATA Services – Student One
Business Development Directorate:
Vocational School of Mining
RPL, Business Development
Academic Unification
Quality Unit
TAFE Directorate (Office of)
Vocational School s of:
Business and Humanities
Engineering and Trades
Academic Learning Service Unit
Train@CQUniversity
Notes: New Council members (Agreement)
New structure new challenges, building capacity for Growth
W footprint new campuses Engagement – regional model
Aligning to existing systems, efficiency not recreating any wheels – still not quite
Smallest Division to one of the Largest Divisions
Previously ALSU, RTO Train@CQUniversity, Metro, QCPD
New Leadership needs new team
Fitting in: Nomenclature and structure
TAFE Directorate – PVC TAFE Dr Greg McMillan
Teaching and Learning
Vocational School
Vocational Deans

## Slide 10: Implementation Group
Academic Unification
Communications
Facilities Management
Finance and Planning
Governance
Information and Technology Systems
Marketing
People and Culture
Student Services
Notes: In no particular order
Interdependencies
Goal, safe transition of business, students, staff, stakeholders, maintain continuity with positive change
Cultures- University independent self administrating –staff and students identify HE
TAFE public servants, public sector centralised administration, staff and students identify VET from 45 years some 27 years no leave
Blind folded, hands tied, gagged, shifting sands, egg timer
For all the right but very frustrating reasons:
Blind folded- limited true sight risk –requests for information
Hands tied- cant do anything until 1 July
Gagged- all communications via group and strictly controlled
Shifting sands- political on off and TAFE Reform
Egg timer- 1 July
Groups chaired by DVC International and service reporting to DS Program Manager (me)
Each chaired by senior managers from CQU and CQTAFE and with DETE representative, minutes reported at each level

## Slide 11: Academic Unification
Key interdependencies:
  Communications
  Governance
  Systems
  Marketing
  Student Services
Notes: Developing mechanisms for new product
Culture
Kim Harrington paper 3

## Slide 12: Communication
  Comprehensive
  Commonwealth and State
  All Stakeholders – roadshows, community events
  Dual Sector HUB
  Media
Notes: VC Coined the phrase, no money for a name change
No dual, not HE and lower
Comprehensive Hub
Tarts

## Slide 13: Facilities Management
  Covenants
  Valuations
  Backlog Maintenance
  Space utilisation
  University Standard
Notes: EIF 1 EIF 3

## Slide 14: Finance and Planning
  Funding:
  transitional and completion
  FYs
  Systems
  Reporting:
  ongoing, aggregate and separate
Notes: Educating everyone
Funding agreements transitional, cap and maintenance ITD and infrastructure, purchasers grant (TAFE- RTO)
Completion agreement debtors, creditors
Contestable market, pre qualified supplier status
Different FYs deliver out 2014 – own 2015
Integrated budget and forecasting
Credit cards, reconciliations, accounting treatment VET staff used to this happening in state
Shared services SLAs

## Slide 15: Governance
  Policy and procedure
    Operational
    Academic
  Safe transfer of all records
  Structures and Committees
  Reporting, quality, compliance
Notes: Rebadge – review too early?
Academic board VTECC VETQ
ASQA
TEQSA
DoE
DETE

## Slide 16: Information and Tech Systems
  Business readiness all systems
  Student One
  Desktops and communications
  LMS
  TM1
  Library, CRM, Timetabling
  Academic Unification
Notes: Across all new campuses
HESA 2
EIF1

## Slide 17: Marketing
  CQUniverse
  Comprehensive
  Website
  QTAC
  Handbook
  New Programs
  Events - open days
Notes: Major re brand
Practical information

## Slide 18: People and Culture
  Managing change
  Safe transfer of all staff
  Fair Work Australia
  JCC Unions
  Copied state instrument
Notes: Academic Professional
Teaching Administrative

## Slide 19: Student Services Experience
  Safe transition of all students
  Open for business
  Write to all students and employers - guides
  Structure call centre
  On message
  Graduations
Notes: Enrolling new students into new system
scripting

## Slide 20: One Glorious CQ day in July 2014…
  It happened:
  Legislation was enacted
  We transferred information
  We transferred staff and students
  Central Queensland celebrated

## Slide 21: 9 months in…
  Change management ongoing
  Dynamic, gradually refining systems and business process
  Gradually integrating core business structures
  All systems gggo…
Notes: Operational changes resulting in system efficiencies, also creates new roles in system config…business areas and shared services

## Slide 22: Evaluation and Impact Analysis
  Vocational Research
  Program evaluation - framework
  Early impact analysis 2016 Benchmarking
  Long term impact
Notes: Symposium
October VET
Scholarships
Research Leader
Project evaluations
HESA 4,5,6 Retention
Easy connect
ALSU Steps and ALCs